PRINCETON PROJECT METHODOLOGY -- PROJECT COMMUNICATION PLAN (rev. 10/03/03)
A well planned project has a well planned Communication strategy. The following are guidelines and options when creating a Project Communication Plan.

What	Who/Target	Purpose	When/Frequency	Type/Method(s)
Initiation Meeting	All stakeholders*	Gather information for Initiation Plan	FIRST / Before Project Start Date	Meeting
Distribute Project Initiation Plan	All stakeholders*	Distribute Plan to alert stakeholders of project scope and to gain buy in.	Before Kick Off Meeting / Before Project Start Date	Document distributed via hardcopy or electronically. May be posted on project website or OIT Blackboard site. / PPM Templates: Project Snapshot or “Lite” Initiation Plan
Project Kick Off	All stakeholders*	Communicate plans and stakeholder roles/responsibilities. / Encourage communication among stakeholders.	At or near Project Start Date	Meeting
Status Reports	All stakeholders and Project Office	Update stakeholders on progress of the project.	Regularly Scheduled. / Monthly is recommended for large/midsize projects.	Distribute electronically and post via web/OIT Blackboard site. / PPM Template: Status Report
Team Meetings	Entire Project Team. / Individual meetings for sub-teams, technical team, and Functional teams as appropriate.	To review detailed plans (tasks, assignments, and action items).	Regularly Scheduled. / Weekly is recommended for entire team. Weekly or bi-weekly for sub-teams as appropriate.	Meeting / PPM Template: Detailed Plan
Project Advisory Group Meetings / (this may apply only to larger projects)	Project Advisory Group and Project Manager	Update Project Advisory Group on status and discuss critical issues. Work through issues and change requests here before escalating to the Sponsor(s).	Regularly Scheduled. / Monthly is recommended.	Meeting
Sponsor Meetings	Sponsor(s) and Project Manager	Update Sponsor(s) on status and discuss critical issues. Seek approval for changes to Project Plan.	Regularly scheduled / Recommended biweekly or monthly and also as needed when issues cannot be resolved or changes need to be made to Project Plan.	Meeting
Executive Sponsor Meetings / (this may apply only to larger projects)	Executive Sponsor(s) and Project Manager	Update Sponsor(s) on status and discuss critical issues. Seek approval for changes to Project Plan.	Not regularly scheduled. / As needed when issues cannot be resolved or changes need to be made to Project Plan.	Meeting
PPO Audit/Review	Project Office, Project Manager, select stakeholders, and possibly Sponsor(s) if necessary.	Review status reports, issues, and risks. To identify and communicate potential risks and issues that may effect the schedule, budget, or deliverables.	Monthly / Scheduled by the Project Office	Meeting/Report / Project Office will produce report using their template.
Post Project Review	Project Office, Project Manager, key stakeholders, and sponsor(s).	Identify improvement plans, lessons learned, what worked and what could have gone better. Review accomplishments.	End of Project or end of major phase	Meeting/Report / Project Office will produce report.
Quarterly Project Review	Project Office, Project Manager, and key stakeholders.	Review overall health of the project and highlight areas that need action.	Quarterly depending on size and criticality of the project. / Scheduled by the Project Office.	Meeting/Report / Project Office will produce report using internal template.
Presentations to Special Interest Groups	Examples: / PMT (Project Managers Team), OIT Leadership Group, AIS Quarterly Review, AMG (Academic Managers Group), etc.	To update external groups to promote communication a create awareness of project interdependencies.	At project milestones so as to communicate with other interested parties of changes that will be introduced outside of the Project Team.	Presentation/Demonstration
OIT Blackboard Site	ALL OIT and OIT Project Team Members.	Central location to house Status Reports, meeting minutes, Project description, and Project Plan. For any communications that can be shared with all OIT staff.	Update monthly with Status Reports; otherwise, as necessary.	Electronic Communications Venue
Periodic Demos and Target Presentations	Specific Focus Groups or End Users. / Examples: / AMG (Academic Managers Group), Students, Power Users, Help Desk, Dept Mgrs., etc.	To gain input from special groups and keep them abreast of the Project’s status.	Once product has enough to “show”. As you complete critical phases or make major enhancements.	Presentation/Discussion
Other…	To be determined by the Project Team	General communications	As needed	PAW, PWB, Lunch n Learns, email lists, PU home page announcements, etc.

*Princeton Project Methodology (PPM) describes stakeholders as: “…any person or group who has a vested interest in the success of the project, i.e. either provides services to the project, or receives services from the project. A key stakeholder is defined as: A person whose support is critical to the project – if the support of a key stakeholder were to be withdrawn, the project would fail.”